## 0. How to use this template
Introduction to the Care Workforce Pathway adoption planning template At this point, your organisation may have decided to run a pilot and/or adopt the Pathway in a way that works for you. This template is designed to support organisations who are at an advanced stage of planning on how to adopt the Pathway. You can access additional Pathway resources and templates, such as the Pathway mapping template, from the <Skills for Care website>. Ideally, you would have read the Guide to Adopting the Pathway document which explains how to think through what would work best for your organisation, before you develop your plan. You may be adopting aspects of the Pathway or its entirety, it’s up to you, which is why this template provides three possible options on a spectrum of light to full adoption which you can adapt: Light Adoption (changes to paperwork), Medium Adoption (changes to processes) and Full Adoption (changes to structure and operating model). For example, a light adoption for you might be aligning only one role category and introducing career conversations and planning for your staff. There is no right or wrong way to adopt the Pathway. The decision is for your organisation and how best the Pathway can help with your overall workforce ambitions and challenges. Smaller organisations with less than 20 staff may have different workforce challenges and limited capacity to set up a Pathway project internally, compared with medium or larger organisation. Therefore, we have included a tailored suggested plan with minimal tasks to help these organisations. The suggested tasks in this Excel are based on the work and feedback by the Early Adopters during the Pathway testing programme. The Pathway is for all adult social care organisations, regardless of size and services provided. We encourage everyone to move towards full adoption overtime, in line with your organisational objectives.
How to use this template: This template provides a simple way for adult social care organisations to create a visual plan of tasks, which can be tracked to support the adoption of the Care Workforce Pathway. There are 6 worksheets/tabs in this Excel workbook. Use the relevant worksheet to support your planning approach for the Pathway. The pre-populated tasks in each adoption plan tab are suggestions, you can keep, remove or edit based on your needs: 1. Pilot Information – if you’re going to pilot the Pathway, you can use this space to think about the scope of your pilot and what you’d like to achieve from piloting it in your organisation. 2. Pathway Pilot Plan – here you’ll find a timeline and task plan with some suggested structure to help you plan. 3. Plan for smaller orgs – this suggested plan is tailored for small organisations with fewer than 20 staff, where the lead person planning for adoption is likely to be the CEO who often is also the Operations and HR lead. 4. Light Adoption Plan – if your organisation has decided to review and align documents with the Pathway and introduce career planning, this suggested plan will help you get started. 5. Medium Adoption Plan – if your organisation wants to review and align people processes with the Pathway, use this plan. Ideally you will also be doing the light adoption tasks or have completed these before adopting at this level. 6. Full Adoption Plan – this plan builds on the light and medium adoption. At this stage your organisation is looking to change role structures and/or operating model to enhance end to end employee lifecycle. In tabs 3 – 6, simply, • Enter your tasks (column B) • Enter assigned owner (column C) • Start date (column E) • End date (column F) • Enter figure for percentage (%) complete (column D) You will see timeline bars automatically appear in the plan representing the duration of the task. These can be tracked based on % completed per task.

## 1. Pilot Information
Care Workforce Pathway - scoping your pilot
1. This worksheet will help you to think about who you would like to be involved with your pilot. This includes the sites and specialisms that would be representative of your wider organisation. 2. You can also note the reasons for wanting to adopt the Pathway, to ensure the pilot outcomes can help address these.
Pathway Pilot Lead/Project Manager | Enter name | Deputy Pilot Lead: | Enter name
Your organisation's reason(s) for piloting the Pathway | What workforce challenge(s) is your organisation looking to address through the Pathway?
What will you be measuring during the pilot? | List the areas you want to test from the pilot. E.g. improvements to job descriptions/adverts, increased staff satisfaction by xx%, increased candidates in recruitment pipeline by xx%, etc…
Region to include in pilot | Site to include in pilot | No. of HR/Ops/L&D teams taking part | No. of managers taking part in pilot group | No. of line reports taking part in pilot group | Specialism
Enter region | Enter site | Enter number | Enter number | Enter number | Enter specialism covered (if applicable)
Enter region | Enter site | Enter number | Enter number | Enter number | Enter specialism covered (if applicable)
Enter region | Enter site | Enter number | Enter number | Enter number | Enter specialism covered (if applicable)
Enter region | Enter site | Enter number | Enter number | Enter number | Enter specialism covered (if applicable)
Enter region | Enter site | Enter number | Enter number | Enter number | Enter specialism covered (if applicable)
Enter region | Enter site | Enter number | Enter number | Enter number | Enter specialism covered (if applicable)
Add more rows as required

## 2. Pathway Pilot plan
Pathway pilot plan
1. The tasks listed below are a suggested structure for how you plan your pilot. 2. You can add, edit or delete tasks/rows to structure the plan as you see fit.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  | Project Start: |  | 2025-01-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02
 | time axis 2025-01-13 to 2026-02-08
| Suggested tasks - add, edit, delete tasks/rows as needed. | ASSIGNED TO enter name | PROGRESS enter % completed | START dd/mm/yy | END dd/mm/yy | DAYS | time axis 2025-01-13 to 2026-02-08
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Pathway pilot governance
| Pilot scope and size (pilot group/sites/settings/specialisms) agreed |  | 0%
| Duration of overall pilot group agreed |  | 0%
| Pilot plan completed |  | 0%
Pathway mapping analysis
| Gather the pre-existing documents such as job descriptions / values / other documents (L&D policy or list of training, H&S policy, etc) to be mapped against the Pathway during the pilot |  | 0%
| Role category A - job mapping |  | 0%
| Role category B - job mapping |  | 0%
| Role category C - job mapping |  | 0%
| Role category D - job mapping |  | 0%
| Role category E - job mapping |  | 0%
| Role category F - job mapping |  | 0%
| Values mapping |  | 0%
| Meeting with senior stakeholders to discuss values mapping |  | 0%
| Review completed templates, share your insights with proposed next steps to Senior Leadership Team |  | 0%
The Pathway as an approach to managing and developing your workforce
| Agree on which team members and their line reports will take part in the pilot (as per your pilot scope in tab '1. Pilot Information') |  | 0%
| Invite to a pilot briefing session, if required, to outline the purpose and exercises for managers and line reports to complete. Send templates to pilot group (e.g., Pathway skill assessment for relevant pilot group roles, career conversations and development toolkits, personal development plans). Share links to the Strengths and Coaching skills learning videos from the Skills for Care website |  | 0%
| Gather pre-exercise insights through a short survey to each line manager to complete ahead doing the exercise and using toolkits and templates. To understand their initial perceptions of a career in adult social care (e.g., 'I see a long term career in adult social care', 'I feel I can support my team with their career goals' 'I feel supported by my organisation', 'I have the information needed to fulfil my own and my team's development' etc) |  | 0%
| Gather pre-exercise insights through a short survey from line reports to complete ahead of using the toolkits and templates. To understand their initial perceptions of a career in adult social care (e.g., 'I see a long term career in adult social care', 'I feel supported by my organisation', 'I have the information needed to fulfill my development', etc) |  | 0%
| Send templates to pilot group (e.g., skill gaps assessments, career development toolkits, personal development plans) |  | 0%
| Give managers and line reports time to complete the skills assessments. Check-in on progress. |  | 0%
| Give managers and line reports time to reflect, meet and have career conversations to develop a career plan. Line managers may need time to prepare for the conversation too. |  | 0%
| Monitor and request copy of completed career development plans and skills assessments |  | 0%
| Provide guidance to line managers on frequency of regular check-ins with line reports to continue having career conversations and coaching the individual to achieve their goals |  | 0%
| Send post-exercise survey to line managers to complete individually following use of toolkits and templates, with same questions as pre-exercise survey to track any changes |  | 0%
| Send post-exercise survey to line reports to complete individually following use of toolkits and templates, with same questions as pre-exercise survey to track any changes |  | 0%
| Review completed career templates and self-assessment to understand demand for development and gaps in workforce knowledge and skills to inform decisions needed at next Pathway Governance meeting |  | 0%
Additional Pathway you would like to pilot beyond those listed above
0%
0%
0%
0%
0%
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows above this one
Note on C4: Author: The Excel automatically shows 8 weeks of the plan. For example, by displaying week 1, you'll see the first 8 weeks., week 2 the following 8 weeks. If you want to see the entire duration of the project, simply add the start and end dates in columns E and F. When completed, make sure the Display Week cell (column E) is left blank.

## 3. Plan for small orgs
Plan for small organisations
1. The tasks listed below are a guide for how you may want to plan your pilot. 2. You can add, edit or delete tasks/rows to structure the plan as you see fit.
|  | Project Start: |  | 2025-01-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26
 | time axis 2025-01-13 to 2026-02-01
| Suggested tasks - add, edit, delete tasks/rows as needed. | ASSIGNED TO enter name | PROGRESS enter % completed | START dd/mm/yy | END dd/mm/yy | DAYS | time axis 2025-01-13 to 2026-02-01
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Pathway mapping analysis
| Gather the pre-existing documents such as job descriptions / values / other documents (L&D policy or list of training, H&S policy, etc) to be mapped against the Pathway |  | 0%
| Complete Mapping template - Role Category A |  | 0%
| Complete Mapping template - Role Category B |  | 0%
| Complete Mapping template - Role Category C |  | 0%
| Complete Mapping template - Role Category D |  | 0%
| Complete Mapping template - Role Category E |  | 0%
| Complete Mapping template - Role Category F |  | 0%
| Collate the gaps identified in relevant documents/policies/manual |  | 0%
| Create group of staff to consult on potential changes to policies, process, etc. |  | 0%
| Update agreed changes to job descriptions |  | 0%
| Update agreed changes to job adverts |  | 0%
| Update agreed changes to other documents (L&D policy, H&S policy etc) |  | 0%
| Review and sign off updated documents |  | 0%
| Communicate to wider organisation on changes |  | 0%
| Publish updated documents internally |  | 0%
| Track improvements to recruitment data (e.g., number/ quality of applications, lower candidate dropout, etc) |  | 0%
Adopting Pathway as an approach to managing and developing your workforce
| Review Pathway resourc+B26:F32es available such as career development toolkits against existing career development guidance and tools |  | 0%
| Select Pathway toolkits, (or at minimum, coaching questions from toolkits for example) to add to current appraisals guidance, documents and policy |  | 0%
| Communicate changes to staff, highlighting this as best practice |  | 0%
| Have staff complete skills self-assessments |  | 0%
| Conduct career conversations with staff |  | 0%
| Have staff complete career development plans |  | 0%
| Upload updated internal packs (e.g. onboarding pack, etc) to relevant systems (e.g. SharePoint, etc) |  | 0%
Additional Pathway suggested tasks you may want to consider, based on light, medium, full adoption
| Consider using Pathway skills self-assessment gaps and career development plan goals to explore further training or targeted recruitment of new staff |  | 0%
| Consider funding Pathway suggested training qualifications for staff |  | 0%
| Consider using Pathway values and behaviours to instil a new culture in your staff, by rewarding and recognising staff who conduct themselves in a similar way listed in the Pathway |  | 0%
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on C4: Author: The Excel automatically shows 8 weeks of the plan. For example, by displaying week 1, you'll see the first 8 weeks., week 2 the following 8 weeks. If you want to see the entire duration of the project, simply add the start and end dates in columns E and F. When completed, make sure the Display Week cell (column E) is left blank.

## 4. Light Adoption plan
Light adoption plan
1. The tasks listed below are a guide for how you may want to plan your pilot. 2. You can add, edit or delete tasks/rows to structure the plan as you see fit.
|  | Project Start: |  | 2025-01-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26
 | time axis 2025-01-13 to 2026-02-01
| Suggested tasks - add, edit, delete tasks/rows as needed. | ASSIGNED TO enter name | PROGRESS enter % completed | START dd/mm/yy | END dd/mm/yy | DAYS | time axis 2025-01-13 to 2026-02-01
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Pathway mapping analysis
| Complete Mapping template - Role Category A (if not complete during a pilot) |  | 0%
| Complete Mapping template - Role Category B (if not complete during a pilot) |  | 0%
| Complete Mapping template - Role Category C (if not complete during a pilot) |  | 0%
| Complete Mapping template - Role Category D (if not complete during a pilot) |  | 0%
| Complete Mapping template - Role Category E (if not complete during a pilot) |  | 0%
| Complete Mapping template - Role Category F (if not complete during a pilot) |  | 0%
| Collate the gaps identified in relevant documents/policies/manual |  | 0%
| Meet with relevant teams (HR/Ops/L&D etc) to facilitate decision-making discussion on addressing any gaps and plan for the agreed updates |  | 0%
| Create group of staff to consult on potential changes to job descriptions (this may only apply if significant changes being introduced) |  | 0%
| Update agreed changes to job descriptions |  | 0%
| Update agreed changes to job adverts |  | 0%
| Update agreed changes to (L&D policy, H&S policy etc) |  | 0%
| Review and sign off updated documents |  | 0%
| Communicate to wider organisation on changes |  | 0%
| Publish updated documents internally |  | 0%
| Track improvements to recruitment data (e.g. number/ quality of applications, lower candidate dropout, etc) |  | 0%
Adopting Pathway as an approach to managing and developing your workforce
| Review Pathway resources available such as career development toolkits against existing career development guidance and tools |  | 0%
| Review feedback from pilot group (if completed) |  | 0%
| Select Pathway toolkits, (or at minimum, coaching questions from toolkits for example) to add to current supervision guidance, documents and policy |  | 0%
| Communicate changes to managers, highlighting this as optional best practice |  | 0%
| Upload updated internal packs (e.g. onboarding pack, etc) to relevant systems (e.g. SharePoint, etc) |  | 0%
| Promote the resources regularly through internal comms channels to support career conversations and development |  | 0%
| Gather feedback from staff on experience of using the Pathway resources to inform any improvements needed to the documents for your organisation |  | 0%
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on C4: Author: The Excel automatically shows 8 weeks of the plan. For example, by displaying week 1, you'll see the first 8 weeks., week 2 the following 8 weeks. If you want to see the entire duration of the project, simply add the start and end dates in columns E and F. When completed, make sure the Display Week cell (column E) is left blank.

## 5. Medium Adoption plan
Medium adoption plan
1. The tasks listed below are a guide for how you may want to plan your pilot. 2. The medium adoption approach builds on the tasks listed in light touch adoption worksheet 3. You can add, edit or delete tasks/rows to structure the plan as you see fit.
|  | Project Start: |  | 2025-01-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  |  |  |  | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19
 | time axis 2025-01-06 to 2026-01-25
| Suggested tasks - add, edit, delete tasks/rows as needed. | ASSIGNED TO enter name | PROGRESS enter % completed | START dd/mm/yy | END dd/mm/yy | DAYS | time axis 2025-01-06 to 2026-01-25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Adopting Pathway into recruitment process - review Pathway values and behaviours
| Review overarching Pathway values and the Pathway behaviours per role category |  | 0%
| Map values and behaviours to your current job adverts |  | 0%
| Map values and behaviours to your current interview questions |  | 0%
| Identify and address gaps in current job adverts and candidate recruitment activities (assessments, interview questions etc) to align with Pathway values and/or behaviours |  | 0%
| Review and confirm with Pathway governance |  | 0%
| Communicate to wider HR / Ops teams and relevant department managers involved with recruitment decisions |  | 0%
Integrating Pathway with existing standard supervision process and reviews
| Review Pathway career development toolkit |  | 0%
| Collate current supervision process toolkits and guidance from across the organisation |  | 0%
| Update the current supervision process to include Pathway career development toolkits/templates to complement existing process |  | 0%
| Choose cadence of Pathway career development toolkit use (e.g., should managers engage in a career conversation on Pathway knowledge and skills at every supervision, or should this be done on a quarterly/ half/ yearly basis?) |  | 0%
| Inform managers of changes to supervision process |  | 0%
| Inform staff of changes to supervision process |  | 0%
| Ask all staff to complete skills self-assessment before supervision or the next objective setting cycle that includes career conversation |  | 0%
| Ask all managers to review skills self-assessment before career conversation or to complete the self-assessment as a joint exercise |  | 0%
| Track career conversation and career development plan completion on regular basis (ideally line report empowered to own their plan with manager as coach) |  | 0%
| Review career development plans to ensure opportunities for development can be planned |  | 0%
| Provide opportunities for development and ask for regular feedback to inform improvements to workforce data |  | 0%
Adopting Pathway's recommended/suggested learning and development
| Review training outlined in Pathway |  | 0%
| Identify alignment and gaps with any existing in-house training |  | 0%
| Decide what training to source externally |  | 0%
| Review and confirm external training / apprenticeship provider(s) |  | 0%
| Plan funding for staff who will undergo training (this can be done in waves to manage staff expectations) |  | 0%
| Plan number and names of staff who will undergo training |  | 0%
| Plan and book backfill for staff whilst they undergo training |  | 0%
| Frequent communication on learning and development opportunities available (courses, on-job-learning, reading/podcasts etc). Gather feedback to inform improvements to packs and the workforce data |  | 0%
| Send workforce on training and ask for regular feedback to inform improvements to workforce data |  | 0%
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on B8: Note: There is no expectation for the Pathway to replace organisation values. The Pathway values can be used as optional to guide attracting the right candidates that align with the values and beliefs that's suited for your organisation.
Note on C4: Author: The Excel automatically shows 8 weeks of the plan. For example, by displaying week 1, you'll see the first 8 weeks., week 2 the following 8 weeks. If you want to see the entire duration of the project, simply add the start and end dates in columns E and F. When completed, make sure the Display Week cell (column E) is left blank.

## 6. Full adoption plan
Full adoption plan
1. The tasks listed below are a guide for how you may want to plan your pilot. 2. The medium adoption approach builds on the tasks listed in light touch adoption worksheet 3. You can add, edit or delete tasks/rows to structure the plan as you see fit.
|  | Project Start: |  | 2025-01-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26
 | time axis 2025-01-13 to 2026-02-01
| Suggested tasks - add, edit, delete tasks/rows as needed. | ASSIGNED TO enter name | PROGRESS enter % completed | START dd/mm/yy | END dd/mm/yy | DAYS | time axis 2025-01-13 to 2026-02-01
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Redesign organisation role structure
| Conduct role analysis and review gaps against Pathway role categories with relevant teams (Ops/HR) to share with Pathway governance |  | 0%
| Consider impact of introducing roles e.g. changes to reporting lines, workflows, how roles work interact etc |  | 0%
| Create job description for new role based on Pathway role category knowledge, skills and behaviours and career development and progression opportunities |  | 0%
| Develop and update organisational charts with clear reporting lines |  | 0%
| Consult with senior leadership team/Pathway governance team, HR/Ops and Union as required |  | 0%
| Update relevant policies and procedures to support new roles and structure. |  | 0%
| Advertise for new role and/or consider who from existing workforce is eligible for promotion into new role |  | 0%
| Gather feedback from workforce and implement lessons learned to ensure new structures works as intended |  | 0%
Adopting Pathway for strategic workforce and succession planning
| Understand existing workforce skills and training - request some or all staff to complete skills self assessment (ideally online e.g. MS Forms) |  | 0%
| Identify existing critical roles and skills needed |  | 0%
| Identify future workforce and skills needs based on organisation goals and industry trends |  | 0%
| Determine number of roles needed and skills needed to meet future care demands |  | 0%
| Conduct analysis between current and future skills to identify areas of development for the workforce |  | 0%
| Develop strategies to address development gaps through learning, recruitment, promotion, etc |  | 0%
| Implement changes and review improvements to workforce data |  | 0%
HR/People systems aligned with Pathway
| Conduct review of HR systems to understand capabilities and where Pathway alignment is needed |  | 0%
| Update systems to ensure Pathway learning and development can be tracked |  | 0%
| Update employee record with Pathway information, e.g. role title, skills, career goals etc |  | 0%
| Align performance management systems with Pathway , as required |  | 0%
| Set up reporting / analytics to identify internal trends, gaps, etc |  | 0%
| HR/Ops/L&D staff trained on updated systems |  | 0%
Organisation culture of continuous learning and development
| Define the culture needed to support workforce development and growth - working with cross section of managers/line reports/leaders to ensure inclusion and equal opportunities too |  | 0%
| Present findings to internal Pathway governance for discussion and approval |  | 0%
| Clear roles and responsibilities with clear actions for leaders/managers and workforce |  | 0%
| Agree reward and recognition for individuals demonstrating behaviours for culture of development and growth |  | 0%
| Ongoing communications to promote the culture with stories from the organisation |  | 0%
| Agreed reward and recognition for individuals demonstrating behaviours for culture of development and growth |  | 0%
| Measure impact of culture on workforce data |  | 0%
Insert new rows ABOVE this one
Note on C4: Author: The Excel automatically shows 8 weeks of the plan. For example, by displaying week 1, you'll see the first 8 weeks., week 2 the following 8 weeks. If you want to see the entire duration of the project, simply add the start and end dates in columns E and F. When completed, make sure the Display Week cell (column E) is left blank.